## Summary
[6 empty] | 2 | 5 | 5 | 4 | 5 | 21
FY2024
| Division | Team | KPI 2024 | Each Month | Apr | May | [5 empty] | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
[6 empty] | 02~03 | 06~10 | 13~17 | 20~24 | 27~31 | Total
| Systems Management Division | FASE | 3.5 | Actual | 3.0067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.675 |  |  |  | KPI rate | 101.1% | 0% | 0% | 0% | 0% | 0% | 0% | bar: Jun to Mar
| Systems Management Division | DIC,MODOS, OSS | 23 | Actual | 19.5698 | 1.91 | 4.6567 | 4.655 | 3.68 | 4.7533 | 19.655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24.15 |  |  |  | KPI rate | 100.1% | 83.04% | 80.99% | 80.96% | 80% | 82.67% | 81.39% | bar: Jun to Mar
| Systems Management Division | HIME | 7 | Actual | 5.555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.35 |  |  |  | KPI rate | 93.36% | 0% | 0% | 0% | 0% | 0% | 0% | bar: Jun to Mar
| Total |  | 33.5 | Actual | 28.1315 | 1.91 | 4.6567 | 4.655 | 3.68 | 4.7533 | 19.655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35.175 |  |  |  | KPI rate | 98.79% | 57.01% | 55.6% | 55.58% | 54.93% | 56.76% | 55.88% | bar: Jun to Mar

## FASE (hidden)
[8 empty] | Actual work days of this month |  |  | 21
May
FASE |  |  |  | 1st week | 2nd week | 3rd week | 4th week | 5th week | Total
|  |  |  | Actual Working Hour | Actual Working Hour | Actual Working Hour | Actual Working Hour | Actual Working Hour |  | Actual work days | ContractMM
|  |  |  | 2 | 5 | 5 | 4 | 5 |  | 21 | 3.5 | * The upper part of "Orange Line : Sub Total(Project Only)" is need to create only Project.
|  |  |  | 02~03 | 06~10 | 13~17 | 20~24 | 27~31 | Total | MM | MM | * The middle part between "Orange Line : Sub Total(Project Only)" and "Red Line : Sub Total(Project and Training/Improvement)" is for Charged Member Training and Improvement by DIR and Internal while waiting reviews or project.
DX推進部 |  |  |  | 52.5 | 131.25 | 131.25 | 105 | 131.25 | 551.25 | 3.675 | 3.5 | * The last part under "Red Line : Sub Total(Project and Training/Improvement)" is DAT Internal Works, Jinwa Training Paid by DAT and Uncharged Member Training.
Project ID | Project Name | Tasks | Plan/Actual
DAT2024-02-12-001-01 | FASE Development | RPA development Orchestrator maintenance | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
DAT2024-02-13-001-01 | 社内SNS Operations and Development | ‐受付者 ‐ユーザー登録．削除 ‐チームメンバー登録．削除 .UUID 作業 ‐事後照査システム(Chatwork)開発・運用 ‐事後照査システム(Teams)開発・運用 | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | Plan | [5 empty] | 0 | 0 | 0
|  |  | Actual | [5 empty] | 0 | 0 | 0 | 0%
|  |  | Plan | [5 empty] | 0 | 0 | 0
|  |  | Actual | [5 empty] | 0 | 0 | 0 | 0%
|  |  | Plan | [5 empty] | 0 | 0 | 0
|  |  | Actual | [5 empty] | 0 | 0 | 0 | 0%
Sub Total(Project Only) |  |  | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
DAT2024-02-12-003-01 | FASE offshore level development and Training | Orchestrator training Windows server administration training | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
DAT2024-02-13-003-01 | 社内_SNS Project Knowledge Improvement and Training | -SNS operation training | Plan | [5 empty] | 0 | 0 | 0
|  |  | Actual | [5 empty] | 0 | 0 | 0 | 0%
|  |  | Plan | [5 empty] | 0 | 0 | 0
|  |  | Actual | [5 empty] | 0 | 0 | 0 | 0%
Sub Total(Project and Training/Improvement) |  |  | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
DAT2018-08-16-002 | JLPT Training Program | Japanese Language Training | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
DAT2021-08-16-005-01 | QC circle | QC Tasks for improving productivity and quality | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
DAT2022-08-29-001-01 | Maintenance of documents for business | Maintenance of documents for business | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
― | Other | DAT Knowledge sharing, Internal meeting, Internal Event, Leave, etc. | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | [5 empty] | 0 | 0 | 0 | 0%
|  |  | Actual | [5 empty] | 0 | 0 | 0 | 0%
Total |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Difference (Contract Vs. Actual) |  |  |  | 52.5 | 131.25 | 131.25 | 105 | 131.25 | 551.25 | 3.675 | 3.5
|  |  |  | Plan | Actual
|  |  | Project | 0 | 0
|  |  | Training | 0 | 0
Note on L6: Calculated with 20 days
Note on M6: Calculated with Acutal Working Day

## DIC (hidden)
[8 empty] | Actual work days of this month |  |  | 21
May
Distributed Infrastructure Construction(DIC) |  |  |  | 1st week | 2nd week | 3rd week | 4th week | 5th week | Total
|  |  |  | Actual Working Hour | Actual Working Hour | Actual Working Hour | Actual Working Hour | Actual Working Hour |  | Actual work days | ContractMM
|  |  |  | 2 | 5 | 5 | 4 | 5 |  | 21 | 5 | * The upper part of "Orange Line : Sub Total(Project Only)" is need to create only Project.
|  |  |  | 02~03 | 06~10 | 13~17 | 20~24 | 27~31 | Total | MM | MM | * The middle part between "Orange Line : Sub Total(Project Only)" and "Red Line : Sub Total(Project and Training/Improvement)" is for Charged Member Training and Improvement by DIR and Internal while waiting reviews or project.
基盤技術第一部 |  |  |  | 75 | 187.5 | 187.5 | 150 | 187.5 | 787.5 | 5.25 | 5 | * The last part under "Red Line : Sub Total(Project and Training/Improvement)" is DAT Internal Works, Jinwa Training Paid by DAT and Uncharged Member Training.
Project ID | Project Name | Tasks | Plan/Actual
DAT2024-02-25-001-01 | DIC Development | KNO Project: Automation Input and Unit test procedre manual creation DBP Project: Automation Input(Common, Node list, OS) and SVK Unit test SPP Project: tools version of JOB materials VLS Project: JCU agent deployment | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | Plan | [5 empty] | 0 | 0 | 0
|  |  | Actual | [5 empty] | 0 | 0 | 0 | 0%
|  |  | Plan | [5 empty] | 0 | 0 | 0
|  |  | Actual | [5 empty] | 0 | 0 | 0 | 0%
|  |  | Plan | [5 empty] | 0 | 0 | 0
|  |  | Actual | [5 empty] | 0 | 0 | 0 | 0%
Sub Total(Project Only) |  |  | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
DAT2024-02-25-002-01 | DIC DIR Training | - Regular Training Meeting | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
DAT2024-02-25-003-01 | DIC Project Knowledge Improvement & Training | -DIC Internal Improvement training | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Sub Total(Project and Training/Improvement) |  |  | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
― | Other | DAT Knowledge sharing,MM Report, Internal meeting, Internal Event, Leave, etc. | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
DAT2018-08-16-002 | JLPT Training Program | -JLPT Training Program | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
― | FOC | -FOC member | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Total |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Difference (Contract Vs. Actual) |  |  |  | 75 | 187.5 | 187.5 | 150 | 187.5 | 787.5 | 5.25 | 5
|  |  |  | Plan | Actual
|  |  | Project | 0 | 0
|  |  | Training | 0 | 0
Note on L6: Calculated with 20 days
Note on M6: Calculated with Acutal Working Day

## MODOS (hidden)
[8 empty] | Actual work days of this month |  |  | 21
May
MODOS |  |  |  | 1st week | 2nd week | 3rd week | 4th week | 5th week | Total
|  |  |  | Actual Working Hour | Actual Working Hour | Actual Working Hour | Actual Working Hour | Actual Working Hour |  | Actual work days | ContractMM
|  |  |  | 2 | 5 | 5 | 4 | 5 |  | 21 | 10 | * The upper part of "Orange Line : Sub Total(Project Only)" is need to create only Project.
|  |  |  | 02~03 | 06~10 | 13~17 | 20~24 | 27~31 | Total | MM | MM | * The middle part between "Orange Line : Sub Total(Project Only)" and "Red Line : Sub Total(Project and Training/Improvement)" is for Charged Member Training and Improvement by DIR and Internal while waiting reviews or project.
基盤技術第一部 |  |  |  | 150 | 375 | 375 | 300 | 375 | 1575 | 10.5 | 10 | * The last part under "Red Line : Sub Total(Project and Training/Improvement)" is DAT Internal Works, Jinwa Training Paid by DAT and Uncharged Member Training.
Project ID | Project Name | Tasks | Plan/Actual
DAT2024-2-14-001-01 | MODOS Development | (VII) - Virus scan engine information checking operation - Certificate information checking operation - TMCM schedule download status checking operation | Plan | 1 | 2 | 2 | 2 | 2 | 9 | 0.06 | 0.057143
|  |  | Actual | 1 | 2 | 2 | 2 | 2 | 9 | 0.06 | 0.057143 | 0.5714%
|  | (IDC/RRS) - IDC User Account Maintenance operation | Plan | 3 | 2 | 2 | 2 | 2 | 11 | 0.073333 | 0.069841
|  |  | Actual | 3 | 2 | 2 | 2 | 2 | 11 | 0.073333 | 0.069841 | 0.6984%
|  | (FASE) - FASE admission form operation - Request operation for permission to use Production environment's servers | Plan | 0 | 2 | 2 | 2 | 2 | 8 | 0.053333 | 0.050794
|  |  | Actual | 0 | 2 | 2 | 2 | 2 | 8 | 0.053333 | 0.050794 | 0.5079%
|  | (UMP) - Past File Acquisition Request Operation(UMP)(#8490) | Plan | 2 | 2 | 2 | 2 | 2 | 10 | 0.066667 | 0.063492
|  |  | Actual | 2 | 2 | 2 | 2 | 2 | 10 | 0.066667 | 0.063492 | 0.6349%
|  | (SVK) For Operation: (1) Creating time table monitoring On/Off operation (2) Creating event calendar operation (3) Checking zabbix01 disk utilization operation (4) Cache Clear operation (Disk usage over 90%) (5) Information collect for URL/Trans monitoring operation (6) Information collect for interval time monitoring operation (7) Creating UMR list operation (8) Docker Container Restart Failed Operation (9) Check weekday and weekend SVKIII JOBNET running status in Toyosu and Tama(#7238) | Plan | 10 | 20 | 20 | 20 | 20 | 90 | 0.6 | 0.57143
|  |  | Actual | 10 | 20 | 20 | 20 | 20 | 90 | 0.6 | 0.57143 | 5.714%
|  | #8826,T0017300(BSS) - JAZ Server Installation - Collecting the required rpms to install Zabbix Server | Plan | 0 | 55 | 55 | 40 | 55 | 205 | 1.3667 | 1.3016
|  |  | Actual | 0 | 55 | 55 | 40 | 55 | 205 | 1.3667 | 1.3016 | 13.02%
|  | #7307,(SVK) -【SVK】 Zabbix Trap Item and Trigger Creation by Tool(ZBX Sender) (Specification, Development, Testing) | Plan | 8 | 55 | 55 | 40 | 55 | 213 | 1.42 | 1.3524
|  |  | Actual | 8 | 55 | 55 | 40 | 55 | 213 | 1.42 | 1.3524 | 13.52%
|  | #8890,A2010000-F0600(SharePoint) - Support for Contents Migration due to Organization Change | Plan | 37 | 37 | 37 | 30 | 37 | 178 | 1.1867 | 1.1302
|  |  | Actual | 37 | 37 | 37 | 30 | 37 | 178 | 1.1867 | 1.1302 | 11.3%
|  | Preparation of acquire new knowledge for upcoming actual tasks - Redmine Environment Construction(V5.1.2) on Rhel9.3 | Plan | 0 | 40 | 40 | 34 | 40 | 154 | 1.0267 | 0.97778
|  |  | Actual | 0 | 40 | 40 | 34 | 40 | 154 | 1.0267 | 0.97778 | 9.778%
|  | Necessary Preparation - #7307(SVK) - #8897,A2010000-U0100(SVK) | Plan | 19.5 | 0 | 0 | 0 | 0 | 19.5 | 0.13 | 0.12381
|  |  | Actual | 19.25 | 0 | 0 | 0 | 0 | 19.25 | 0.12833 | 0.12222 | 1.222%
|  | Project Management (Team, Tasks, Meeting, Discussion, Reports, Issues, etc.,) | Plan | 5 | 0 | 0 | 0 | 0 | 5 | 0.033333 | 0.031746
|  |  | Actual | 5 | 0 | 0 | 0 | 0 | 5 | 0.033333 | 0.031746 | 0.3175%
|  | #8840,(SVK) -【OOO】 Request for change of department name | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  | (JCU) - JOB Center Tool Modification | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  | (Sharepoint & PA Flow) - Investigate about sharepoint access permission due to department changing - Investigate about UFA record list inconsistency problem - R&D for PA flow suspend due to inactive - Discuss about Support for Contents Migration due to Organization Change | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  | - Learning and discussion about Quality control management | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  | #8890,A2010000-F0600(SharePoint) - Support for Contents Migration due to Organization Change | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  | #8897,A2010000-U0100(SVK) - Creation of SVKIII version of monitoring state traffic congestion map (For April) | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  | Project Management (Team, Tasks, Meeting, Discussion, Reports, Issues, etc.,) | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Sub Total(Project Only) |  |  | Plan | 85.5 | 215 | 215 | 172 | 215 | 902.5 | 6.0167 | 5.7302
|  |  | Actual | 85.25 | 215 | 215 | 172 | 215 | 902.25 | 6.015 | 5.7286 | 57.29% | 56.83% | 57.33% | 57.33% | 57.33% | 57.33%
DAT2024-2-14-003-01 | MODOS Project Knowledge Improvement & Training | - Offshore Certification Training | Plan | 12 | 30 | 30 | 24 | 30 | 126 | 0.84 | 0.8
|  |  | Actual | 12 | 30 | 30 | 24 | 30 | 126 | 0.84 | 0.8 | 8%
DAT2024-2-14-003-01 | MODOS Project Knowledge Improvement & Training | - Getting project knowledge improvement from past projects - Training for projects - Support for New Members | Plan | 52.5 | 130 | 130 | 104 | 130 | 546.5 | 3.6433 | 3.4698
|  |  | Actual | 52.75 | 130 | 130 | 104 | 130 | 546.75 | 3.645 | 3.4714 | 34.71%
Sub Total(Project and Training/Improvement) |  |  | Plan | 150 | 375 | 375 | 300 | 375 | 1575 | 10.5 | 10
|  |  | Actual | 150 | 375 | 375 | 300 | 375 | 1575 | 10.5 | 10 | 100%
DAT2018-08-16-002 | JLPT Training Program | Japanese Language Training | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
DAT2022-08-16-006-01 | Staff Improvement Trainings | C Training | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
DAT2021-08-16-005-01 | QC circle | QC Tasks for improving prductivity and quality | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
DAT2022-08-29-001-01 | Maintenance of documents for business | Maintenance of documents for business | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
― | Other | DAT Knowledge sharing, Internal meeting, Internal Event, Leave, etc. | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
― | un-charge members | Training for Unchargeable Member | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Total |  |  |  | 150 | 375 | 375 | 300 | 375 | 1575 | 10.5 | 10 | 100%
Difference (Contract Vs. Actual) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Plan | Actual
|  |  | Project | 5.7302 | 5.7286
|  |  | Training | #REF! | #REF!
Note on L6: Calculated with 20 days
Note on M6: Calculated with Acutal Working Day

## OSS
[8 empty] | Actual work days of this month |  |  | 21
May
OSS |  |  |  | 1st week | 2nd week | 3rd week | 4th week | 5th week | Total
|  |  |  | Actual Working Hour | Actual Working Hour | Actual Working Hour | Actual Working Hour | Actual Working Hour |  | Actual work days | ContractMM
|  |  |  | 2 | 5 | 5 | 4 | 5 |  | 21 | 8 | * The upper part of "Orange Line : Sub Total(Project Only)" is need to create only Project.
|  |  |  | 02~03 | 06~10 | 13~17 | 20~24 | 27~31 | Total | MM | MM | * The middle part between "Orange Line : Sub Total(Project Only)" and "Red Line : Sub Total(Project and Training/Improvement)" is for Charged Member Training and Improvement by DIR and Internal while waiting reviews or project.
基盤技術第一部 |  |  |  | 120 | 300 | 300 | 240 | 300 | 1260 | 8.4 | 8 | * The last part under "Red Line : Sub Total(Project and Training/Improvement)" is DAT Internal Works, Jinwa Training Paid by DAT and Uncharged Member Training.
Project ID | Project Name | Tasks | Plan/Actual
DAT2024-02-27-001-01 | OSS Development | A2025500-B0000 Customer Inquires Support (For all released version 2.0~6.1.1) JAZ 2.1.1 & 6.0 - Investigation for 1119, 1121, 1122, 1126,1136,1137, 1139, 1175, 1174, 1179 | Plan | 52.5 | 112.5 | 75 | 75 | 112.5 | 427.5 | 2.85 | 2.7143
|  |  | Actual | 55.25 | 102.6 | 68.75 | 76.25 | 112.65 | 415.5 | 2.77 | 2.6381 | 32.98%
DAT2024-02-27-001-01 | OSS Development | A2025500-C0000 JAZ 6.1.1 Development (JAZ 6.1.1) '- Bug Fix - Unit Test Spec Modification - Unit Test Execution | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
DAT2024-02-27-001-01 | OSS Development | A2025500-C0000 JAZ 6.0.4 Development Unit Testing - Coding Development - Basic Design Creation - Bug fix - Code review - Testing. | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
DAT2024-02-27-001-01 | OSS Development | A2025500-C0000 JAZ 7.0 Frontend Development | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
DAT2024-02-27-001-01 | OSS Development | A2025500-C0000 JAZ 7.0 Backend Development | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
DAT2024-02-27-001-01 | OSS Development | A2025500-C0000 JAZ 6.0.5.1 Development - Environment preparation. - RPM Creation Development - #1046 UI and error logs enhancement for zabbix api - #1045 PHP version error on setup screen Unit Testing - Testing | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
DAT2024-02-27-001-01 | OSS Development | A2025500-C0000 JAZ 6.1.5.1 Development - Environment preparation. - Bug Fix - Release notes list up - RPM Build - JAZ Home Page Manual Update | Plan | 52.5 | 150 | 187.5 | 135 | 150 | 675 | 4.5 | 4.2857
|  |  | Actual | 50.7 | 152.15 | 198.5 | 140.15 | 156.25 | 697.75 | 4.6517 | 4.4302 | 55.38%
DAT2024-02-27-001-01 | OSS Development | A2025500-E0000 Project Management(Team meeting, daily progress report cretion, WBS creation, issue management, Translation) | Plan | 15 | 37.5 | 37.5 | 30 | 37.5 | 157.5 | 1.05 | 1
|  |  | Actual | 17.55 | 43.75 | 28.25 | 35.6 | 33.85 | 159 | 1.06 | 1.0095 | 12.62%
Sub Total(Project Only) |  |  | Plan | 120 | 300 | 300 | 240 | 300 | 1260 | 8.4 | 8
|  |  | Actual | 123.5 | 298.5 | 295.5 | 252 | 302.75 | 1272.25 | 8.4817 | 8.0778 | 101% | 102.9% | 99.5% | 98.5% | 105% | 100.9%
DAT2024-02-27-003-01 | OSS Project Knowledge Improvement and Training | Offshore certificate level up training. (Web Client Level 2 training) | Plan | 1.5 | 0 | 0 | 0 | 0 | 1.5 | 0.01 | 0.0095238
|  |  | Actual | 7.25 | 0 | 0 | 0 | 0 | 7.25 | 0.048333 | 0.046032 | 0.5754%
DAT2024-02-27-003-01 | OSS Project Knowledge Improvement and Training | Offshore certificate level up training. (C or Go Level 2 training) | Plan | 1.5 | 7.5 | 3.75 | 0 | 0 | 12.75 | 0.085 | 0.080952
|  |  | Actual | 3 | 9 | 2 | 0 | 0 | 14 | 0.093333 | 0.088889 | 1.111%
DAT2024-02-27-003-01 | OSS Project Knowledge Improvement and Training | Offshore certificate level up training. (Frontend Level 3 training) | Plan | 1.5 | 0 | 0 | 0 | 0 | 1.5 | 0.01 | 0.0095238
|  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 13.5
DAT2024-02-27-003-01 | OSS Project Knowledge Improvement and Training | New Member Supporting | Plan | 1.5 | 3.75 | 0 | 0 | 0 | 5.25 | 0.035 | 0.033333
|  |  | Actual | 2.75 | 4.25 | 0 | 0 | 0 | 7 | 0.046667 | 0.044444 | 0.5556%
DAT2024-02-27-003-01 | System Maintenance Course | System Design & knowledge sharing - signal handling, Unix Domain Socket, Pipe | Plan | 4.5 | 11.25 | 26.25 | 0 | 37.5 | 79.5 | 0.53 | 0.50476
|  |  | Actual | 0 | 11.75 | 25.75 | 0 | 35.25 | 72.75 | 0.485 | 0.4619 | 5.774%
DAT2024-02-27-003-01 | Automation | Unit Testing & E2E testing | Plan | 4.5 | 0 | 0 | 0 | 0 | 4.5 | 0.03 | 0.028571
|  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Sub Total(Project and Training/Improvement) |  |  | Plan | 135 | 322.5 | 330 | 240 | 337.5 | 1365 | 9.1 | 8.6667
|  |  | Actual | 136.5 | 323.5 | 323.25 | 252 | 338 | 1373.25 | 9.155 | 8.719 | 109%
DAT2018-08-16-002 | JLPT Training Program | Japanese Language Training | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DAT2021-08-16-005-01 | QC circle | QC Tasks for improving prductivity and quality | Actual | 0 | 4 | 0 | 0 | 1 | 5 | 0.033333 | 0.031746 | 0.3968%
― | Other | DAT Knowledge sharing, Internal meeting, Internal Event, Leave, etc. | Actual | 0 | 24.5 | 14 | 4.5 | 10.5 | 53.5 | 0.35667 | 0.33968 | 4.246%
― | Un-charge Member | - New Member Training - Performance Testing for jobarranger server and proxy - Testing for External command in proxy server and connector | Actual | 15.5 | 36.25 | 37.75 | 67.5 | 25.5 | 182.5 | 1.2167 | 1.1587 | 14.48%
DAT2022-08-29-001-01 | Maintenance of documents for business | Genral and System related document listup | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
DAT2022-08-16-006-01 | Staff Improvement Trainings | C Trainings | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | Actual | [5 empty] | 0 | 0 | 0 | 0%
Total |  |  |  | 152 | 388.25 | 375 | 324 | 375 | 1614.25 | 10.7617 | 10.2492 | 128.1%
Difference (Contract Vs. Actual) |  |  |  | -32 | -88.25 | -75 | -84 | -75 | -354.25 | -2.3617 | -2.2492
|  |  |  | Plan | Actual
|  |  | Project | 8 | 8.0778
|  |  | Training | 0.038095 | 0.077778
Note on L6: Calculated with 20 days
Note on M6: Calculated with Acutal Working Day

## HIME (hidden)
[8 empty] | Actual work days of this month |  |  | 21
May
Host Infrastructure Maintenance(HIME) |  |  |  | 1st week | 2nd week | 3rd week | 4th week | 5th week | Total
|  |  |  | Actual Working Hour | Actual Working Hour | Actual Working Hour | Actual Working Hour | Actual Working Hour |  | Actual work days | ContractMM
|  |  |  | 2 | 5 | 5 | 4 | 5 |  | 21 | 7 | * The upper part of "Orange Line : Sub Total(Project Only)" is need to create only Project.
|  |  |  | 02~03 | 06~10 | 13~17 | 20~24 | 27~31 | Total | MM | MM | * The middle part between "Orange Line : Sub Total(Project Only)" and "Red Line : Sub Total(Project and Training/Improvement)" is for Charged Member Training and Improvement by DIR and Internal while waiting reviews or project.
基盤技術第二部 |  |  |  | 105 | 262.5 | 262.5 | 210 | 262.5 | 1102.5 | 7.35 | 7 | * The last part under "Red Line : Sub Total(Project and Training/Improvement)" is DAT Internal Works, Jinwa Training Paid by DAT and Uncharged Member Training.
Project ID | Project Name | Tasks | Plan/Actual
DAT2024-02-21-001-01 | HIME Opeation(定型タスク) | Tasks which has code lines ・O生命VOL管理台帳の更新(124, 138,171) ・O生命VOLバックアップJOBの修正 (117,147) ・(社保)配布先マスターの変更作業の引継ぎ (118,123, 137, 151,155,160,165,170,173, 177) ・VOL追加に伴うJCL修正(2VOL追加) (130, 134, 136, 140,162,168) ・(外販)帳票印刷数のカウントPython(111) ・(SONAR-MF)銀行マスタの更新Python(115) | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
DAT2024-02-21-001-01 | HIME Opeation(定型タスク) | Tasks which haven't code lines. ・(外販)帳票印刷数のカウント(111) ・(SONAR-MF)銀行マスタの更新(115) | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
DAT2024-02-21-001-01 | HIME Development(通常案件) | SMART DB自動化レベルアップ (106,143,152,153,156) | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
DAT2024-02-21-001-01 | HIME Development(通常案件) | SMART ATOM自動化レベルアップ (113,148) | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
DAT2024-02-21-001-01 | HIME Development(通常案件) | SMART DB/ATOM業務案件 (154,158,161,169) | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
DAT2024-02-21-001-01 | HIME Development(余裕がある場合) | ・ASHサーバーPython化詳細設計書作成と保守対応作業(53_C0517800) ・CPU使用率監視メールの死活監視 (159_C0517800) | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
DAT2024-02-21-001-01 | HIME Development(通常案件) | MSTX95(TSOユーザIDマスタ)の週次更新 | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
DAT2024-02-21-001-01 | HIME Development(通常案件) | SMARTのDB定義変更関連(172,174) | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
DAT2024-02-21-001-01 | HIME Development(通常案件) | SMARTクライアント無影響試験準備(175) | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
DAT2024-02-21-001-01 | HIME Development(通常案件) | チャンネル運用の停止( SMART,MARK), ATOMリソース資源の抹消(176) | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub Total(Project Only) |  |  | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
DAT2024-02-21-003-01 | HIME Project Knowledge Improvement and Training | Acquire Knowledge Sharing Knowledge HIME Internal Skill Up | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
DAT2024-02-21-003-01 | HIME Project Knowledge Improvement and Training | DIR Internal Tasks(THiNC account,SW list,Report…) | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Sub Total(Project and Training/Improvement) |  |  | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
DAT2020-08-16-004-01 | Staff Development Program(Training) | Japanese Language Training | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
DAT2018-08-16-002 | JLPT Training Program | JLPT Training Program | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
DAT2021-08-16-005-01 | QC circle | QC Tasks for improving prductivity and quality | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
DAT2022-08-16-006-01 | Staff Development Program(Training) | Staff Improvement C Trainings | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
DAT2023-08-07-001-01 | DAT Internal Tools | Email Sending Tool Modification Tax Calculation Tool | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
DAT2022-08-29-001-01 | Maintenance of Documents for Business | DAT Internal Management | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
― | Other | DAT Knowledge sharing, Internal meeting, Internal Event, Leave, etc. | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
DAT2022-08-16-002-01 | Intensive OJT Program_2023 | Intensive OJT Program_2023 | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Total |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Difference (Contract Vs. Actual) |  |  |  | 105 | 262.5 | 262.5 | 210 | 262.5 | 1102.5 | 7.35 | 7
|  |  |  | Plan | Actual
|  |  | Project | 0 | 0
|  |  | Training | 0 | 0
Note on L6: Calculated with 20 days
Note on M6: Calculated with Acutal Working Day

## Template History (hidden)
Template History | [6 empty] | If you change or update template, you have to fill history in the content
No. | Version | Effected Date | Person In-Charge | Action | Effected Sheets | Description
1 | template ver 1.0 | 2022-05-04 | Kyi Saw Win | Create | All sheets in template | Created standard template for Weekly MM Reprot. Purpose : To reduce workload. Changed : 1. Deleted "Data" Sheet. 2. Deleted "Summary" Sheet. 3. Modified equation for General MM and Actual Working Day MM. 4. Added Plan Row. 5. Added Plan and Actual Status Graphs.